## Start here
Dabur International Digital: project tracker
Suhail's digital marketing team: MENA and SSA, with support for India, Egypt, Turkey (Hobby) and Pakistan.
How to use it
1 | Find your own tab (Suhail, Nour, Sanya, Khushii). Only you and Suhail can edit your tab.
2 | Add one row per project. Pick Market, Brand, Stream and Status from the dropdowns.
3 | When something changes, rewrite "Latest update / next step" and set "Last updated" to today (Ctrl + ; types today's date).
4 | If you are stuck or need Suhail, set Status to Blocked and write what you need in "Blocked on / need from Suhail".
5 | For updates, ideas, learnings, deck links or questions, add a row in the Comments tab. Everyone can write there.
6 | To comment on any single cell, on any tab, right-click it and choose Comment. Type @ and a name to email that person.
The tabs
Dashboard | Suhail's overview: counts per person and market, what is overdue or blocked, latest comments. Fills itself in.
All projects | Every project from every person's tab in one list. Fills itself in, so don't type here.
Your tab | Your projects. This is the only place you add or change a project.
Comments | Shared notes for the whole team, including Manish and Nishant. Suhail replies in the last column.
Lists | The dropdown values (markets, brands, streams, agencies). Ask Suhail to add a new brand or agency.
Colours
Red row | Overdue: the due date has passed and the project is not done.
Amber row | Blocked: waiting on someone or something.
Grey text | Done.
Orange date | Last updated more than 14 days ago.

## Dashboard
Dashboard
Fills itself in from everyone's tabs. Active means not done. Overdue means past the due date and not done.
By person
Person | Active | In progress | Blocked | Overdue | Due in next 14 days | Done
Team total
By market
Market | Active | In progress | Blocked | Overdue | Due in next 14 days | Done
Needs attention: overdue or blocked
Owner | Project | Market | Status | Due date | Blocked on / need from Suhail
Due in the next 14 days
Owner | Project | Market | Status | Due date | Latest update / next step
Latest comments
Date | Who | Project | Type | Comment | Reply from Suhail

## All projects
All projects |  | Fills itself in from each person's tab. Don't type here; change projects on the owner's tab.
Owner | Project | Market | Brand | Stream | Status | Due date | Latest update / next step | Blocked on / need from Suhail | Agency | Link (brief, deck, folder) | Last updated

## Suhail
Suhail | Only Suhail and Suhail can edit this tab. One row per project; use the dropdowns.
Project | Market | Brand | Stream | Status | Due date | Latest update / next step | Blocked on / need from Suhail | Agency | Link (brief, deck, folder) | Last updated
Hobby Kenya Micro Dramas Shoot | SSA |  |  | In progress | 2026-10-12 | Storyboard First cut ready, Main Cast locked, Support cast WIP, Production location WIP, Agreement with creators WIP. PPM date to be locked. Travel Approvals to be taken and ready. Final Shoot date - 19, 21, 22, 23 (4 Day Shoot) |  | Creative Stitch |  | 2026-10-04
Enhance digital marketing |  |  | Big Bets | Done | [5 empty] | 2026-10-02
Gemini / AI in the team's work |  |  | AI Projects | In progress | [5 empty] | 2026-10-02
Note on A2: Source: Dabur Digital Network hub (claude.ai artifact), exported 7 Oct 2026.

## Nour
Nour | Only Nour and Suhail can edit this tab. One row per project; use the dropdowns.
Project | Market | Brand | Stream | Status | Due date | Latest update / next step | Blocked on / need from Suhail | Agency | Link (brief, deck, folder) | Last updated
100k Giveaway Influencer Iraq, Jordan | MENA |  | Influencer Marketing | In progress | 2026-10-21 |  |  | Sagerlabs |  | 2026-10-04
Iraq Mega Influencers Campaign (EHO+ SHAMPOO) | MENA | Vatika | Influencer Marketing | Not started | 2026-10-30 | Influencer to receive the products |  |  |  | 2026-10-07
KSA BULK DEAL - BODYWASH | MENA | Vatika Bodywash | Influencer Marketing | In progress | 2026-10-30 | Reviewing the videos and adding feedback |  |  |  | 2026-10-07
KSA HOBBY STORE VISIT | MENA | Hobby | Influencer Marketing | In progress | 2026-10-30 |  |  |  |  | 2026-10-07
MOROCCO - MISWAK BULK DEAL | MENA | Dabur Miswak | Influencer Marketing | In progress | 2026-10-30 |  |  |  |  | 2026-10-07
SWAVY - WOWTIKA | MENA | Multi-brand | Influencer Marketing | In progress | 2026-10-30 |  |  |  |  | 2026-10-07
Vatika Bodywash Cafe Collab | MENA |  | Digital Activations | In progress | 2026-11-30 |  |  | Anphonic |  | 2026-10-04
THE VATIKA HOUSE | MENA | Multi-brand | Big Bets | In progress | 2027-02-01 |  |  |  |  | 2026-10-07
INTERN ROOM REVAMP |  |  |  | In progress | [5 empty] | 2026-10-07
Note on A2: Source: Dabur Digital Network hub (claude.ai artifact), exported 7 Oct 2026.

## Sanya
Sanya | Only Sanya and Suhail can edit this tab. One row per project; use the dropdowns.
Project | Market | Brand | Stream | Status | Due date | Latest update / next step | Blocked on / need from Suhail | Agency | Link (brief, deck, folder) | Last updated
100K Giveaway Social Creative | MENA |  | Social Media Management | In progress | 2026-10-05 |  |  | Saturday Communication |  | 2026-10-07
100K Giveaway Infl UAE, KSA, North Africa | MENA |  | Influencer Marketing | In progress |  |  |  | Anphonic |  | 2026-10-04
100k Giveaway Infl Kuwait | MENA |  |  | In progress |  |  |  | Ghost Agency |  | 2026-10-04
Note on A2: Source: Dabur Digital Network hub (claude.ai artifact), exported 7 Oct 2026.

## Khushii
Khushii | Only Khushii and Suhail can edit this tab. One row per project; use the dropdowns.
Project | Market | Brand | Stream | Status | Due date | Latest update / next step | Blocked on / need from Suhail | Agency | Link (brief, deck, folder) | Last updated

## Team member 4
Team member 4 | For the fourth team member: change the name in A1 and rename this tab. Only they and Suhail can edit it.
Project | Market | Brand | Stream | Status | Due date | Latest update / next step | Blocked on / need from Suhail | Agency | Link (brief, deck, folder) | Last updated

## Comments
Comments |  | Everyone can write here. Newest at the bottom; the Dashboard shows the latest 10. Suhail replies in column G.
Date | Who | Project (or General) | Type | Comment | Link | Reply from Suhail

## Lists
Markets | Brands | Streams | Status | Agencies | People | Comment types
MENA | Multi-brand | Performance Marketing | Not started | Anphonic | Suhail | Update
SSA | Dabur Amla | Influencer Marketing | In progress | Creative Stitch | Nour | Idea
India | Vatika | Content Creators | Blocked | Ghost Agency | Sanya | Learning
Egypt | Dabur Red | Social Media Management | Done | Sagerlabs | Khushii | Expectation
Turkey (Hobby) | Dabur Herb'l | Website / Tech |  | Saturday Communication | Team member 4 | PPT / deck
Pakistan | Herbolene | SEO / GEO |  |  | Manish | Question for Suhail
Multi-market | Hobby | AI Projects |  |  | Nishant | Urgent flag
Internal | Fem | Big Bets
| ORS Olive Oil | Digital Activations
| Dermoviva | Digital Production
| Honitus | ORM
| Dabur Chyawanprash | Others
| GenZ LIC & Serum | Dashboards
| Vatika Curls | Sentiment Analysis
FreshNUp
Herbolene Lotion
Vatika Bodywash
Amla Batana
Amla Rosemary
Vatika Menz Hair Cream
Vatika Sciencification
Vatika Batana Range
Vatika Rosemary Range
Vatika Hair Masks
Vatika Onion Range
Herbolene Pet Jelly Blue
Fem Razors
Vatika Kit Color
Vatika Hair Spray
Fem HRC
Dabur Miswak